## Slide 1: Overall state of progress of the MMR Twinning project Nadine Allemand, MS Project Leader, CITEPA

## Slide 2: Content of presentation
General information:
  Main figures
  Main project objectives
  Beneficiaries
  Project team
  Links with other MRV project
  Expected results per components
State of the progress:
  Overall state of progress
  Achievement of mandatory results
  Deliverables prepared up to date
  Expert working days conducted up to day

## Slide 3: Main figures
Starting date: 15 May 2015
Duration: 24 months
Budget: 1,2 M€ (IPA2012), BC is co-financing 16,7% (0,2M€)
Activities performed up to now: progress at 52%

## Slide 4: Main project objectives
The overall objective of the project is to assist Serbia to meet environmental and climate Acquis through institutional building and improvement of the environmental reporting.
The purpose of the project is to ensure alignment with EU Climate Aquis and fulfillment of the UNFCCC requirements through introduction of a mechanism for monitoring and reporting GHG emissions and for reporting other information relevant to climate change on regular basis.

## Slide 5: Beneficiaries
The main beneficiaries of the project are the Ministry of Agriculture and Environmental Protection, in particular the Climate Change Division and the Serbian Environmental Protection Agency.
In addition, beneficiaries of the project results are other government institutions, relevant ministries and agencies, Statistical Office of the Republic of Serbia, local communities and NGOs.

## Slide 6: The Team
 | Ministry of Environment, Energy and the Sea (MEEM)
 | Interprofessionnal Technical Centre for Studies on Air Pollution (CITEPA)
 | Expertise France
 | Slovenian experts from the Ministry of Agriculture and Environment Belgium expert from the Flemish government

## Slide 7: Links with other twinning on MRV
+ Sectoral measures (CO2 and cars, CO2 and vans, F-Gases, Fuel quality directive, CO2 labelling for cars)
ETS
Effort Sharing Decision
Monitoring Mechanism Regulation
Twinning SR 12 IB EN 01
(completed in sept 2015)
On going Twining SR 13 IB EN 01

## Slide 8: Expected results of the project
Component 1: “Institutional and procedural arrangements for implementation of Monitoring mechanism regulation and Decision 406/2009 established”
Component 2: “Legal framework for implementation of the Regulation (UE) 525/2013 and the monitoring and reporting requirements of Decision 406/2009/EC established”
Component 3: “Administrative and institutional capacities of the relevant bodies in the field of climate change strengthened”

## Slide 9: Overall state of progress
Final Closing Conference
Kick-off Workshop and Initial Assessment Report
Analysis of existing institutional and organisational structure
Recommendations for appropriate institutional and organisational structure , data flows, responsibilities and tasks
Development of draft legal acts
Action plan for legal framework
QA/QC procedures for national inventory system
Rules and procedures to ensure appropriate data flows and timely submission
Guidance on development of GHG inventory and inventory report and MMR deliverables
Training needs assessment and training programs
Training for GHG inventory team
Training for preparation of MMR deliverables
5 days study visit in France
Adoption by the government
Act. 1.1
Act. 1.2
Act. 1.3
Act. 3.1
Act. 3.4
Act. 3.2
Act. 2.2
Act. 2.1
Act. 1.5
Act. 1.4
Act. 3.3










## Slide 10: Achievement of mandatory results
Chart: Overall state of progress- QR4
| Result 0 | Result 1 | Result 2 | Result 3 | Overall
 | 0.5 | 0.1125 | 0 | 0 | 0.15313
 | 0.5 | 0.51563 | 0 | 0 | 0.25391
 | 0.5 | 0.8625 | 0.125 | 0.05 | 0.38438
 | 0.5 | 0.9925 | 0.535 | 0.05 | 0.51937

## Slide 11: Deliverables prepared up to date
      SWOT ANALYSIS FOR IMPLEMENTATION OF THE MMR
      COST-BENEFIT ANALYSIS FOR THE IMPLEMENTATION OF THE MMR
      ASSESSMENT AND RECOMMENDATION REPORT
      SCREENING OF THE LEGAL FRAMEWORK
      QA/QC PROCEDURES FOR THE NATIONAL INVENTORY SYSTEM
      ACTION PLAN FOR MMR LEGAL FRAMEWORK

## Slide 12: Expert working days
Chart: Expert days used per quarter
| QR1 | QR2 | QR3 | QR4
Activity 1.1. | 41 | 47.5 | 0 | 0
Activity 1.2. | 38 | 0
Activity 1.3. | 9 | 36.5 | 4.5
Activity 1.4. | 17 | 13.5
Activity 2.1. | 25 | 10
Activity 2.2. | 5 | 37
Activity 3.1 | 4.5

## Slide 13: Expert working days
Expert working days performed | QR1 | QR2 | QR3 | QR4
Activity 1.1. | 41 | 47,5 | 0 | 0
Activity 1.2. |  | 38 | 0 | 0
Activity 1.3. |  | 9 | 36,5 | 4,5
Activity 1.4. |  |  | 17 | 13,5
Activity 2.1. |  |  | 25 | 10
Activity 2.2. |  |  | 5 | 37
Activity 3.1 |  |  |  | 4,5
Total | 41 | 94,5 | 83,5 | 69,5
Sum Total |  | 135,5 | 219 | 288,5
      Expenditures up to date (Q1+Q2+Q3+Q4) = 514.866 €
      Overall budget allocated in the OSL5 (Q5+Q6) = 308.213€
      After 1 year of the project :
      43% of the budget is spent
      288,5 WDs are used
      19/29 (65%) of the mandatory benchmarks are achieved

## Slide 14: State of progress
Thank you for your attention!
  For further information :
  nadine.allemand@citepa.org Phone : + 33 1 44 83 68 83